## Call flow
Three Point Estimation
Type | Solution | Number | Hour | Simple | Medium | Complex | Cut effort
Simple | Flow iteration | 1-5 | 8 | 2 | 2 | 1
| Webservice | 0 |  | 16 | 48 | 40 | 104
| FAQ | 5
Medium | Flow iteration | 5-7 | 24
| Webservice | 1
| FAQ | 5
| Xfer to agent | 1
Complex | Flow iteration | 5-10 | 40
| Language | 2
| Webservice | 1
| FAQ | 5
| Xfer to agent | 1

## Assumption
We've assumed all the existing live chat converations for Chatbot which is XXXX Interactions per month
Average 25 Interacions needed per conversations
Setting up of 2 environments are considered for the estimates (Dev and PROD)
Assumed 150-200 Intent development
Only English Language has been considered for the efforts
Only text bot functionality is Considered and not Voice bot
No database is considered for environment
10000 interactions has been considered for Dev and Testing

## Chatbot - Component
Bottom Up Estimation
Cuteffort
Category | Evaluation Question | Type | If not given, consider? | Hours | Client RFP
Enviroment | Does the enviroment access be private or cloud. VPN? Restriction on Libraries. | Medium | NO | 16
Data | Do we have to extract data from chat system and store/use in other organization data repositories | Medium | NO | 24 | Y
Agent Xfer | Need to perform peamless handoff with the interaction history to view | Complex | YES | 40
Integration | Integrate with 3rd party system. Are APIs details available? | Complex | YES | 16
API | Is the software REST Enabled | Simple | NO | 8
API | Authenticate process and parameters for it | Simple | NO | 4
API | Access data regarding chat via an API for reporting purposes | Simple | NO | 8
API | Screen pop when connect agents. Do client have API's to pass information from bot. | Medium | YES | 16
Chat Analytics/Reports (OOB) | Client need - Reporting availabie on whom the consumers/users of chat are | Simple | YES | 8
Chat Analytics/Reports (OOB) | Chat operator/agent wait time, handling etc reports | Simple | YES
Chat Analytics/Reports (OOB) | Performance of Live chats and chat bot features available | Simple | YES
Chat Analytics/Reports (OOB) | Schedule, live monitoring, Survey feature | Simple | YES
Chat Analytics/Reports (Custom) | Client need - Reporting availabie on whom the consumers/users of chat are | Complex | NO | 40
Chat Analytics/Reports (Custom) | Chat operator/agent wait time, handling etc reports | Complex | NO
Chat Analytics/Reports (Custom) | Performance of Live chats and chat bot features available | Complex | NO
Chat Analytics/Reports (Custom) | Schedule, live monitoring, Survey feature | Complex | NO
Bot | Multi lingual capabilities required | Medium | YES | 16
Voice Bot | Xfer to live agent in voice channel. CTI | Medium | YES | 16
Advanced Bot | Text based Channel integration. Number of channel. Rich UI | Medium | NO | 8
Advanced Features (OOB) | Chat to Call switch, click to call, trigger outbound | Medium | NO | 8
Advanced Features (OOB) | Skill based routing of call/chat (OOB) | Medium | YES | 16
Advanced Features | Chat Rating - survey? | Medium | NO | 16
Advanced Features(OOB) | Operator Monitoring - Allows management to monitor chat operators and provides insights on which operators are performing | Medium | NO | 12
Advanced Features | Hint Responses - Allows for most frequently used text/questions as hints | Complex | NO | 40
Advanced Features | File Transfer - Allows ability to transfer files between chat and user | Medium | NO | 16
Advanced Features | More than one - Third Party Integrations - Integration with current business tools (e.g., CRM, Outlook, ServiceNow) | Medium | NO | 16
Advanced Features | Is there Customer Support - 24/7 support from chat vendor | Simple | NO | 4
Advanced Features | After hours handling | Simple | NO | 4
Advanced Features | List of channel i.e app, FB, Alexa, Telephone etc | Medium | NO | 16
Infrastructure/Privacy/Security | Mask all PII/PCI/PHI information. | Medium | NO | 8
Infrastructure/Privacy/Security | chat over encrypted connection (SSL) | Medium | NO | 8
Infrastructure/Privacy/Security | Back up plan and recovery options. DR | Complex | NO | 36
Infrastructure/Privacy/Security | Active Firewall to account for cloud based solution | Medium | NO | 32
Branding Requirements | Integrate into existing portals or external channel | Medium | NO | 8