## Effort
Conversational IVR/ Chatbot Effort Summary
Activity | Development Unit Effort | Number of Call flow | Total Efforts | Cut Effort
|  |  |  | Activities | Dev | QA/Pre Prod | Prod
Translator for multi lang | 40 | 4 | 160 | Chatbot Dev | 484 |  | 96.8
Bot development - Simple Flow | 8 | 2 | 16 | NLP | 40 |  | 8
Bot development - Medium Flow | 24 | 2 | 48 | CC platform - Integration | 0 |  | 0
Bot development -Complex Flow | 40 | 1 | 40 |  | 524 |  | 104.8
Webservice ( extra) | 0 |  | 0
Tuning | 20 | 5 | 100
Web page UI development | 20 | 1 | 20 |  |  |  | PH | PD | PW
Integration to Chat | 20 | 5 | 100 |  |  | Total Effort | 628.8 | 78.6 | 15.72
|  | Total | 484
[5 empty] | Phases | PH | PD | PW
|  |  |  | 10% | Requirement Gathering | 140 | 17.5 | 3.5
|  |  |  | 15% | Design | 210 | 26.25 | 5.25
|  |  |  | 45% | Development | 628.8 | 78.6 | 15.72
|  |  |  | 25% | SIT | 349 | 43.625 | 8.725
|  |  |  | 5% | UAT & Go Live | 70 | 8.75 | 1.75
|  |  |  | 100% | Total | 1397.8 | 174.725 | 34.945
[5 empty] | Warranty Support | 120 | 15 | 3
[5 empty] | Total Effort | 1517.8 | 189.725 | 37.945

## RL
| PH | PW | Phases | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Requirement Gathering | 140 | 3.5 | Requirement Gathering
Design | 210 | 5.25 | Design
Development | 628.8 | 15.72 | Development
SIT | 349 | 8.725 | SIT
UAT & Go Live | 70 | 1.75 | UAT & Go Live
Warranty Support | 120 | 3 | Warranty Support
37.945
[17 empty] | PW | PD | PH | Level | Rate
|  |  | Technical Architect Onshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 10 | 50 | 400 | M | 100 | 40000
|  |  | Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 10 | 50 | 400 | M | 30 | 12000
|  |  | Sr Dev | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 10 | 50 | 400 | SA | 25 | 10000
|  |  | Dev |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 6 | 30 | 240 | A | 20 | 4800
|  |  | Sr. Tester | [7 empty] | 1 | 1 | 1 |  |  |  | 3 | 15 | 120 | SA | 25 | 3000
|  |  | Tester | [7 empty] | 1 | 1 |  |  |  |  | 2 | 10 | 80 | A | 20 | 1600
|  |  | Support | [10 empty] | 1 | 1 | 1 | 3 | 15 | 120 | A | 10 | 1200
|  |  | Support | [13 empty] | 41 | 205 | 1640 |  |  | 71400
[21 empty] | Travel & Stay | 3500
[21 empty] | Total TCV | 74900

## Assumption - New
Developing new call scripts in XYZ Platform for 5 use case scenario shared.
Consider 2 Simple, 2 Medium and 1 complex call flow
Design and developing NLU
Development of NLU capability for 5 use case scenario shared.
Development of possible response when intent is triggered by integrating with decision and third party engine via webservice.
Use existing system to pass of variable like call types, variables and data to agent desktop application.
Only IVR (TFN based) or Text channel consider for solution. XYZ Platform will be in use
Efforts are estimated for 2 environments (Test and Production)
No custom reports have been considered for the estimates (Only OOB)
Web services are readily available to consume
No warranty supported is included in the estimates
Only English language is considered in the scope
Hardware and Licensing cost would be extra
Infra costing of port , server cost will be extra
User Acceptance Testing will be done by the business and only UAT Support will be provided by us.
Test Data is readily available for testing and it would be provided by client
Features implemented would be dependent on the product features available with XYZ Platform Capability
These costs are derived based on Onshore + Offshore implementation model
Onsite Location would be XYZ and Offshore location would be in Pune
All the system access and sign off on the requirements will be provided on time

## Assumption - Migration
Existing solution environment is XYZ Platform with all the components of contact center.
Client will provide the necessary information, documents and application walkthroughs for the existing contact center applications relevant for this project implementation and scope.
The following documents will be expected for ‘As-Is’ applications during definition scope phase to deliver the outputs:
Business Requirements
Functional Specifications
Technical Designs
Test Cases (If possible)
Integration Landscape and Specifications
Design Standards at Client
Security Standards to be followed as per Client
Non-functional requirements
Built in and third party tools used in contact center and their licenses applicable to be extended.
End to end contact center technical architecture depicting integration between various components
Concurrent agents split across channels under different geographic locations
It is assumed that IVR will only have English as supported languages
All Hardware, Software and licenses are already available before the start of development
Existing security module would be re-used to avoid building module from scratch
Standard reporting available as part of XYZ Platform would be utilized where ever possible
Post requirement gathering and analysis, estimates will be visited again if there is difference which can't be accommodated with the current estimate
User Acceptance Testing will be done by the business and only UAT Support will be provided by us.
Client need to procure NLP solution Licenses
Understanding of existing self-service scripts, routing and Queuing scripts.
Use existing routing logic in queue based from regular skill based routing.